## Project Plan
Project Name: Eye-Refer
Module | Start Date | End Date | Estimated Hours | Actual Hours | Developer | Status
Modules/Tasks | [5 empty] | Status
Milestone 1 | 2024-12-09 | 2024-12-22
Sprint #1 - Project setup, architecture flow and setup, Mockups and design | 2024-12-09 | 2024-12-15 | 80
Project setup for frontend: |  |  | 4
React with Type-script, Redux, React Query and UI packages
Common components setup
Private / Public routing setup
Loader setup, Validation setup, Eslint setup
Redux toolkit and rest API custom hook setup
Project setup for backend: |  |  | 4
API module ( Backend setup )
Common Module setup
Middleware setup
Architecture and schema setup as per HIPAA Compliance (both admin and web)
Configuration and enviornment setup
Component and routing setup
JWT Auth protected APIs
Project deployment on the staging server |  |  | 8
Deployment of the frontend web application
Deployment of the frontend APIs
Swagger Setup for API documentation
Database and schema creation |  |  | 5
Setup the Database and create the schema for company, plan, and other required tables.
Mockups Design/HTML creation
Landing Page, Authentication pages, and Post-Subscription Banner. |  |  | 16
Create a New Company Form, Guide Section, Plan Section and Forecast Plan Page. |  |  | 33
Template Selector Page. |  |  | 14
Sprint #2 - Authentication, Authorization, and Intial user interactions pages. | 2024-12-16 | 2024-12-22 | 80
User Authentication and Sign-Up
- Sign in with Google. |  |  | 6
- Email and password-based login/sign-up. |  |  | 3
- Forgot Password and reset password functionality. |  |  | 3
Authentication(APIs)
API for User Sign-Up |  |  | 4
API for User Login |  |  | 3
API for Third-Party Login (Google) |  |  | 6
API for Forgot Password |  |  | 3
API for Reset Password |  |  | 4
Landing Page
- Introduction (platform’s purpose and features.) |  |  | 4
- Pricing: Subscription plans and respective pricing. |  |  | 4
- Blog': Add a section with articles, guides, or insights on creating business plans. |  |  | 3
Landing Page (APIs)
Fetch a list of articles, guides, or insights for the blog section. |  |  | 7
Post-Subscription Banner
- Questionnaires (considering the provided questions:) |  |  | 8
Post-Subscription Banner (Questionnaires APIs)
API to Save Questionnaire Responses |  |  | 8
API to Save Each Question's Response in questionnaire |  |  | 4
API to Fetch Questionnaire Responses |  |  | 3
API to Update Questionnaire Responses |  |  | 4
API to Update Each Question's Response in questionnaire |  |  | 3
Milestone 2 | 2024-12-23 | 2025-01-05
Sprint #3 – Company creation, Guide and Plan subscription | 2024-12-23 | 2024-12-29 | 80
Code deployment on the staging server
Deployment of the frontend web application |  |  | 4
Deployment of the frontend APIs |  |  | 4
Swagger update for APIs |  |  | 1
Unit testing and code review |  |  | 1
Company module:
Add company Form |  |  | 6
Edit company Form |  |  | 6
View company Modal |  |  | 4
Company (APIs)
API to Create a New Company |  |  | 6
API to Edit a Company |  |  | 6
API to View Company Details |  |  | 2
API to List Companies(if Required) |  |  | 2
Guide Section
- Full-page section with introductory text explaining the purpose and flow of creating a business plan. |  |  | 7
- Provide video tutorial or quick start guide on the top. |  |  | 1
Guide Section (API)
API to Fetch Guide Content |  |  | 4
Pricing and Subscription
Page where user will select the price and subscribe to any one subscription plan. |  |  | 2
Pricing and Subscription (APIs)
API to Fetch Pricing Plans |  |  | 4
API to Subscribe to a Plan |  |  | 4
Payment gateway |  |  | 16
Sprint #4 – Payment gateway and Business Plan creation | 2024-12-30 | 2025-01-05 | 80
Pricing and Subscription (APIs)
Payment gateway webhooks and other scenarios handling |  |  | 8
Plan Section: |  |  | 40
Content View:
- Full-page editable interface displaying all sections of the business plan.
- Allows scrolling to view and edit the plan in sequence.
- Multiple sections: client will suggest
Plan Section (APIs) |  |  | 32
API to Fetch Business Plan
API to Fetch Business Plan sections
Milestone 3 | 2025-01-06 | 2025-01-05
Sprint #5- Business Plan creation | 2025-01-06 | 2025-01-12 | 80
Plan Section: |  |  | 40
Section Editing Features:
- Include inline text editors for content, with formatting options (e.g., bold, italics).
Live Preview:
- Add a “Save Draft” button to store progress.
- Include a “Download & Print” button to export the business plan as a PDF.
- Include a “preview” button to see how the BP is going to see in a document.
Plan Section (APIs) |  |  | 40
API to Save Draft
API to Export Plan as PDF
API for Live Preview
Sprint #6- Forecast Plan Page | 2025-01-13 | 2025-01-19 | 80
Revenue Overview: |  |  | 24
- Add a chart displaying "Revenue by Month" for the selected year.
Navigation and Toggles:
- Add tabs for switching the financial plan inputs: "Revenue", "Direct Costs", "Personnel", "Expenses", etc.
- Include toggle switches for switching between "Charts", "List", and "Table" views of revenue data.
Add Revenue Stream Functionality:
- Add a prominent button ("+ Add Revenue Stream") to create new streams.
- Integrate with the previously defined revenue stream functionality.
- Allow users to view, edit, or delete existing revenue streams from a list or table view.
General Suggestions and Help:
- Add a "Get Suggestions" link to provide automatic recommendations for revenue streams.
- Add a "Read Instructions" link to guide users through the revenue input process.
Revenue Stream |  |  | 24
- Revenue Stream Name (text input).
- Revenue Stream Type (options: "Unit Sales", "Billable Hours", "Recurring Charges", "Revenue Only").
Unit Sales Functionality: Implement specific fields and logic for "Unit Sales" revenue type:
- Input for defining how the number of units sold is entered:
- Constant Amount or Varying Amounts Over Time.
- Input for defining the number of units sold per period (e.g., month, quarter, year).
- Input for unit price:
- Constant Price or Varying Prices Over Time.
Billable Hours Functionality: Implement fields for "Billable Hours" revenue type:
- Input for how billable hours are entered:
- Constant Amount or Varying Amounts Over Time.
- Input for hourly rate:
- Constant Rate or Varying Rates Over Time.
Recurring Charges Functionality: Implement fields for "Recurring Charges" revenue type:
- Input for start date of the revenue stream (month/year).
- Input for the number of new customers expected per period:
- Constant Amount or Varying Amounts Over Time.
- Input for upfront fees:
- No Fee, Constant Fee, or Varying Fees Over Time.
- Input for recurring charge price:
- Constant Price or Varying Prices Over Time.
- Input for charge frequency (e.g., every X months).
Revenue Only Functionality: Implement fields for "Revenue Only" type:
- Input for defining total revenue:
- Constant Amount or Varying Amounts Over Time.
- Input for specifying the revenue amount per period (e.g., monthly, quarterly).
General Manage Revenue Streams:
- Add functionality to Save & Exit.
- Allow users to Edit and Delete existing revenue streams.
- Implement Auto-Save functionality for data entries.
Revenue (APIs) |  |  | 32
Add revenue stream.
Edit revenue stream.
Delete revenue stream.
Fetch all revenue streams.
Milestone 4 | 2025-01-20 | 2025-02-02
Sprint #7 – Direct Costs and Personnel module | 2025-01-20 | 2025-01-26 | 80
Direct Cost |  |  | 21
1. Direct Cost Name: Text input for naming the cost (e.g., Rent, Raw Materials).
2. Cost Type: Radio button options for specifying the type of cost:
- General Cost: Not tied to a specific revenue stream.
- Cost for a Specific Revenue Stream: Linked to one of the defined revenue streams.
3. Cost Entry Method: Radio button options for defining how the cost is entered:
- Constant Amount ($): Fixed value per period.
- Varying Amounts Over Time ($): Custom values for different periods.
- Constant % of Overall Revenue: A fixed percentage of total revenue.
- Varying % of Overall Revenue: Percentage that changes over time.
4. Cost Amount: Numeric input for specifying the cost value.
5. Frequency: Dropdown to select the frequency of the cost (e.g., per month, per quarter).
6. Start Date: Dropdown for selecting when the cost begins (e.g., January 2024).
General Save and Manage Costs:
- Add a "Save & Exit" button to save the cost and return to the overview.
- Implement a "More Actions" dropdown for editing, duplicating, or deleting the cost entry.
Direct Costs (APIs)
Add direct cost. |  |  | 8
Edit direct cost. |  |  | 8
Delete direct cost. |  |  | 1
Fetch all direct costs. |  |  | 2
Personnel |  |  | 21
1. Personnel Type: Radio button to specify the type of personnel:
- Individual: For adding a single employee or contractor.
- Group of Employees: For adding a team or multiple employees at once.
2. Is This Direct Labor?: Radio button options to specify whether the personnel is direct labor:
- Regular Labor: General employees or contractors not directly tied to production or revenue.
- Direct Labor: Personnel whose costs vary with revenue or production volume.
3. Employment Type: Radio button options to define the type of employment:
- On-Staff Employee: Salaried employees, with payroll taxes and benefits applied automatically.
- Contract Worker: Contractors responsible for their own taxes and benefits.
4. Salary Entry Method: Radio button to select how salaries are entered:
- Constant Amount: Fixed salary amount.
- Varying Amounts Over Time: Custom salary values for different periods.
5. Payment Amount: Numeric input to define the payment amount.
6. Frequency: Dropdown to select payment frequency (e.g., per month, per year).
7. Start Date: Dropdown to specify when payments begin.
8. Annual Raises: Optional numeric input to define percentage increase in salary over time.
General Save and Manage Personnel:
- Add a "Create & Exit" button to save the personnel details and return to the overview.
- Include a "More Actions" dropdown for editing, duplicating, or deleting personnel entries.
Personnel (APIs)
Add personnel (individual or group). |  |  | 8
Edit personnel. |  |  | 8
Delete personnel. |  |  | 1
Fetch personnel data. |  |  | 2
Sprint #8 – Expenses and Assets module | 2025-01-27 | 2025-02-02 | 80
Expenses |  |  | 22
1. Expense Name: Text input for naming the expense (e.g., Rent, Marketing).
2. Entry Method: Radio buttons to define how the expense will be entered:
- Amounts ($): Direct numeric input for expense amount.
- % of Overall Revenue: Calculates expense as a percentage of total revenue.
- % of Specific Revenue Stream: Links expense to a specific revenue stream.
3. Amount Type: Radio buttons to define the type of amount:
- Constant Amount: Fixed value per period.
- Varying Amounts Over Time: Different amounts for specific periods.
- One-Time Amount: Single expense entry for a specific date.
4. Expense Amount: Numeric input for specifying the cost.
5. Frequency: Dropdown to select payment frequency (e.g., per month, per quarter).
6. Start Date: Dropdown to specify when the expense starts.
7. Expense Category: Radio buttons to classify the expense:
- Rent or Lease
- Marketing
- Other Expense
General Save and Manage Expenses:
- Add a "Save & Exit" button to save the expense details and return to the overview.
- Include functionality to edit, duplicate, or delete expense entries.
Expenses (APIs)
Add expense. |  |  | 8
Edit expense. |  |  | 8
Delete expense. |  |  | 1
Fetch all expenses. |  |  | 1
Assets |  |  | 22
1. Asset Name: Text input for naming the asset (e.g., Equipment, Vehicle).
2. Entry Method: Radio buttons to define how the asset cost will be entered:
- One-Time Amount ($): Single cost for the asset.
- Constant Amount ($): Fixed cost over time.
- Varying Amounts Over Time ($): Custom values for different periods.
3. Cost and Purchase Date: Numeric input for asset cost and dropdown for specifying the purchase date.
4. Asset Type: Radio buttons to classify the asset:
- Long-Term Asset: Fixed assets with lasting value, such as equipment or buildings.
- Current Asset: Short-term assets like service contracts or materials.
5. Useful Life: Dropdown to select the asset’s lifespan (e.g., 3 years, 5 years).
6. Do You Plan to Resell This Asset?: Toggle to specify whether the asset will be sold.
- If Yes, additional fields appear:
- Resell Price: Numeric input for the expected selling price.
- Resell Date: Dropdown to specify when the asset will be sold.
General Save and Manage Assets:
- Add a "Create & Exit" button to save asset details and return to the overview.
- Include functionality to edit, duplicate, or delete asset entries.
Assets (APIs)
Add asset (one-time, constant, or varying cost). |  |  | 8
Edit asset. |  |  | 8
Delete asset. |  |  | 1
Fetch all assets. |  |  | 1
Milestone 5 | 2025-02-03 | 2025-02-16
Sprint #9 - System Integration & deployment | 2025-02-03 | 2025-02-09 | 80
Tax Rate |  |  | 16
1. About Income Taxes: Display an informational section explaining income taxes and their impact on financial plans.
2. Estimated Tax Rate: Numeric input for specifying the overall tax rate percentage (e.g., 20%).
3. Payment Frequency: Dropdown to select how often taxes will be paid (e.g., Ǫuarterly, Annually).
General Save and Manage Taxes:
- Add an "Exit" button to save the tax rate and return to the overview.
- Include functionality to update or reset tax rates if needed.
Tax Rate (APIs)
Set tax rate. |  |  | 1
Fetch current tax rate. |  |  | 1
Update or reset tax rate. |  |  | 2
Dividents Paymanets |  |  | 24
1. Dividend Name: Text input for naming the dividend (e.g., Ǫuarterly Payout).
2. Entry Method: Radio buttons to define how the dividend will be calculated:
- One-Time Amount ($): Single distribution.
- Constant Amount ($): Fixed amount distributed periodically.
- Varying Amounts Over Time ($): Custom values for different periods.
- % of Net Profit: Percentage of net profit distributed as dividends.
3. Distribution Amount and Date:
- Numeric input for specifying the distribution amount.
- Dropdown for selecting the distribution date (e.g., January 2024).
General Save and Manage Dividends:
- Add an "Exit" button to save dividend details and return to the overview.
- Include functionality to edit, duplicate, or delete dividend entries.
Dividends (APIs)
Add dividend. |  |  | 8
Edit dividend. |  |  | 8
Delete dividend. |  |  | 1
Fetch dividend details. |  |  | 1
Cash Flow Assumptions (APIs) |  |  | 8
Add assumptions for inflow/outflow. |  |  | 8
Edit/delete assumptions. |  |  | 1
Fetch all assumptions. |  |  | 1
Sprint #10 - System Integration & deployment | 2025-02-10 | 2025-02-16 | 80
Cash Flow Assumptions |  |  | 24
1. Projected Cash Charts:
- A monthly "Projected Cash in FY" line chart showing expected cash flow.
- A yearly "Projected Cash by Year" bar chart for an overview of annual cash flow.
2. Summary Metrics: Display key financial data such as:
- Revenue
- Net Profit
- Cash at the end of the fiscal year
- Expenses & Costs
Accounts Receivable Settings:
3. Sales on Credit Slider:
- Allow users to define the percentage of sales made on credit using a slider (e.g., 0% to 100%).
4. Days to Get Paid Slider:
- Let users configure the average time (in days) it takes to collect payments (e.g., 0 to 180 days).
5. Adjust Individual Revenue Stream Assumptions: Checkbox to enable customizing these settings per revenue stream.
Accounts Payable Settings:
6. Purchases on Credit Slider:
- Define the percentage of purchases made on credit.
7. Days to Pay Slider:
- Set the average time (in days) to pay suppliers.
8. Adjust Individual Expense Assumptions: Checkbox to enable customizing these settings per expense category.
Inventory Settings:
9. Inventory Toggle: Switch to enable or disable inventory management assumptions.
General Save and Manage Cash Flow Assumptions:
- Add a "Save & Exit" button to save assumptions and return to the overview.
- Include functionality to edit or reset cash flow assumptions.
Initial Balance |  |  | 3
1. Summary Display:
- Show calculated totals for Total Assets, Total Liabilities, and Total Equity.
- Ensure the formula Assets = Liabilities + Equity is dynamically validated and displayed.
2. Tabs for Balance Categories: Include tabs to navigate between:
- Initial Assets
- Initial Liabilities
- Total Equity
Initial Assets Section: |  |  | 4
- Cash: Numeric input for the starting cash balance.
- Accounts Receivable: Input for customer balances from past credit sales.
- Days to Get Paid: Dropdown for specifying the time to collect on initial receivables (e.g., 15 days).
- Inventory: Numeric input for the value of unsold inventory.
- Long-Term Assets: Input for the value of fixed assets (e.g., buildings, equipment).
- Accumulated Depreciation: Numeric input for depreciation already claimed on long-term assets.
- Depreciation Period: Dropdown for selecting the length of time to depreciate remaining value.
- Other Current Assets: Input for other assets (e.g., prepaid expenses).
- Amortization Period: Dropdown for selecting how long to expense other assets (e.g., 1 month, 12 months).
General Navigation and Actions:
- Add a "Continue to Liabilities" button to save and move to the next tab.
- Include a "Read Instructions" link to provide detailed guidance on each field.
Initial Liabilities Section |  |  | 4
1. Accounts Payable: Numeric input for the balance owed to suppliers for past purchases on credit.
2. Days to Pay: Dropdown to specify the time required to pay off the initial accounts payable (e.g., 15 days).
3. Income Taxes Payable: Input for any accrued income taxes owed as of the starting date.
4. Sales Taxes Payable: Input for sales taxes collected but not yet remitted to the government.
5. Prepaid Revenue: Auto-calculated field based on prepaid balances set during revenue configuration.
6. Short-Term Debt: Input for balances from loans or credit lines due within 12 months.
7. Long-Term Debt: Input for loans or other financing not due within 12 months.
Actions for Initial Liabilities: |  |  | 4
- Include a "Back to Assets" button for navigation.
- Add a "Continue to Equity" button to save and proceed to the equity section.
- Provide a "Read Instructions" link for help with input fields.
Initial Equity Section: Add a form for defining equity components with the following fields:
1. Paid-In Capital: Input for money invested in the company by owners or stakeholders.
2. Retained Earnings: Auto-calculated value to balance the equation Assets = Liabilities + Equity.
General Integration and Data Sync:
- Synchronize initial balances with the financial plan, including cash flow, balance sheet, and P&L statements.
- Update total assets, liabilities, and equity dynamically across the platform.
Initial Equity Form: |  |  | 4
1. Basic Overview: Display a real-time calculation of Total Assets, Total Liabilities, and Total Equity at the top.
2. Fields for Input: Include the following fields for user input:
- Paid-in Capital: Editable field for user-entered amount of investment by owners.
- Retained Earnings: Automatically calculated based on other data entered in the Initial Balances section.
3. Instructions Panel: Include a help panel on the side or below, explaining each field and its significance.
4. Navigation Buttons: Add Back to Liabilities and Next (to Projections) buttons for seamless flow.
General Auto-Balance Functionality:
Ensure the system keeps the balance between assets, liabilities, and equity by adjusting retained earnings automatically.
Projected Profit & Loss Overview: |  |  | 20
1. Dynamic Chart Integration: Display charts at the top showcasing Net Profit trends and P&L by year.
2. Data Table Layout: Provide a detailed breakdown for:
- Revenue
- Direct Costs (leading to Gross Profit and Gross Margin).
- Operating Expenses
- Operating Income and Income Taxes
- Total Expenses, Net Profit, and Net Profit Margin.
3. Monthly and Annual Toggle: Option to switch between monthly and yearly details with a simple toggle button.
4. Editable Sections: Users can directly edit any field (e.g., Operating Expenses) and see the updates dynamically.
5. Add New Button: Provide flexibility to add custom expense/revenue line items dynamically.
6. Cash Flow Impact Button: Add a clickable button to view cash flow impact based on P&L changes.
Profit & Loss Statement (APIs)
Add assumptions for inflow/outflow. |  |  | 8
Edit/delete assumptions. |  |  | 8
Fetch all assumptions. |  |  | 1
Milestone 6 | 2025-02-17 | 2025-02-02
Sprint #11 - System Integration & deployment | 2025-02-17 | 2025-02-23 | 80
Projected Balance Sheet Overview: |  |  | 16
1. Interactive Data Table: Show yearly columns (2024, 2025, 2026) with dynamic updates for:
- Assets (Current Assets and Long-Term Assets)
- Liabilities & Equity (Current Liabilities, Long-Term Liabilities, Equity)
2. Subcategories: Enable collapsible/expandable categories such as Current Assets, Long-Term Assets, etc.
3. Set Initial Balances Button: Allow users to input starting balances linked to the "Initial Balances" step.
4. Add New Button: Flexibility to create new asset or liability lines dynamically.
5. Monthly and Annual View Toggle: Option to view balances monthly or yearly.
6. Dynamic Summary Panel: Update totals for Revenue, Net Profit, and Cash in real-time at the top.
Balance Sheet (APIs) |  |  | 16
Add assumptions for inflow/outflow.
Edit/delete assumptions.
Fetch all assumptions.
Projected Cash Flow Overview |  |  | 16
- Displays the cash flow projections of the business, including monthly and yearly breakdowns of cash inflows and outflows.
- Key Elements:
1. Cash Flow Summary: Monthly and annual breakdowns, including revenue, net profit, and cash balance at year-end.
2. Key Metrics:
- Net Cash from Operations: Reflects core business activities.
- Net Cash from Investing: Tracks cash used or generated from investments.
- Net Cash from Financing: Includes loans, equity injections, and dividends.
3. Balance: Displays opening and closing cash balances.
4. Adjustments: Options to modify assumptions for receivables, payables, and inventory changes.
- Includes the "Set Cash Flow Assumptions" button to refine projections.
Cash Flow Statement (APIs) |  |  | 16
Add assumptions for inflow/outflow.
Edit/delete assumptions.
Fetch all assumptions.
Financing |  |  | 16
1. Projected Cash Chart:
- Monthly line chart showing expected cash inflows and outflows from financing activities.
2. Financing by Year Chart:
- Bar chart summarizing financing inflows for each year.
3. Summary Metrics:
- Revenue
- Net Profit
- Cash at the End of FY
- Expenses & Costs
4. Financing Table:
- Interactive table to add and display financing details by year.
- Columns for years (e.g., 2024, 2025, 2026) and financing categories (e.g., Loans, Investments).
5. Add Financing Dropdown: Dropdown with options for:
- Loan
- Investment
- Line of Credit
- Other
Create New Loan Form
1. Loan Name: Text input to identify the loan.
2. Loan Receipt Date: Dropdown to specify when the loan amount will be received.
3. Loan Amount: Numeric input for the loan principal amount.
4. Monthly Payment Term: Numeric input for the number of monthly payments to be made.
5. Interest Rate Type: Radio buttons to select:
- Constant Rate: Fixed interest rate for the loan duration.
- Variable Rate: Fluctuating interest rate based on market conditions.
6. Interest Rate: Numeric input for the interest rate percentage.
General Save and Manage Financing Data:
- Add a "Create & Exit" button to save financing inputs and return to the dashboard.
- Allow for editing, duplicating, and deleting financing records.
Sprint #12 - System Integration & deployment | 2025-02-24 | 2025-03-02 | 200
Business Plan Structure |  |  | 24
- Key Features:
1. Editable Sections: Each section is fully customizable (edit, remove, or add). Users can adjust content to fit their unique needs.
2. Design Options: Allows the choice between narrative text (for detailed explanations) or tabular formats (for numerical or structured data).
3. AI-Assisted Writing: Integrated AI offers suggestions, templates, and auto-completion for efficient and professional drafting.
4. Key Points to Include:
- Executive Summary: Overview of the business, including mission, vision, and goals.
- Problem & Solution: Articulates the problem the business solves and the unique solution offered.
- Market Analysis: Market size, target audience, customer segmentation, and competitive landscape.
- Business Model: Revenue streams, cost structure, and value proposition.
- Marketing & Sales Strategy: Channels, pricing, promotions, and customer acquisition plans.
- Operations Plan: Operational workflow, key activities, partnerships, and resources.
- Team & Management: Details on the team, roles, and expertise.
- Financial Plan: Revenue forecasts, expenses, cash flow, and profitability projections.
5. AI-Powered Insights: Suggestions and automatic formatting to optimize the readability and professionalism of the document.
6. Exportable Format: The finalized plan can be exported to PDF or shared online.
AI Implimentation:
Developing an AI engine capable of generating tailored content for various tasks, including rephrasing, grammar correction, professional tone adjustments, and persona-based content customization. |  |  | 40
Integrating dynamic business or organizational data into the AI model, enabling context-aware content generation through advanced prompt engineering techniques |  |  | 40
Creating a chat engine to facilitate real-time queries, providing insights on market trends or business intelligence by leveraging GPT models and internet-sourced data |  |  | 40
Financial Outputs |  |  | 16
API to calculate and fetch projected income statement dynamically.
API to generate a balance sheet based on entered data.
API to compute cash inflows and outflows over a specified period.
API to calculate and fetch key financial ratios (e.g., profitability, liquidity).
Template Selector: where users can search and filter from a variety of predefined business plan templates to kickstart their plan. |  |  | 24
- Key Features:
1. Search Bar: Allows users to search for templates based on keywords, industries, or business types (e.g., tech, retail, hospitality).
2. Filters: Users can filter templates by categories such as:
- Industry: Technology, Food & Beverage, Healthcare, etc.
- Business Model: Subscription-based, e-commerce, service-based.
- Complexity Level: Basic, Intermediate, Advanced.
- Premium/Free: Allows users to filter templates based on access tiers.
3. Template Cards: Each template is displayed as a card showing:
- Template name.
- A short description.
- Preview button.
- Tags (e.g., Premium, Free).
4. Editing Capabilities: Once a template is selected, users can fully customize it. All sections, design elements, and content are editable.
5. Premium Templates: Certain advanced or industry-specific templates are marked as "Premium" and require an upgrade to access.
6. Bookmark & Favorites: Users can save templates to their "Favorites" for easy access in the future.
7. Integrated Tutorials: For beginners, each template includes a step-by-step guide or tips to help users get started.
Templates (APIs) |  |  | 16
Fetch All Templates
Get Template by ID
Add/Edit/Delete Templates (Admin Only) (if required)
Milestone 7 | 2025-03-03 | 2025-03-16
Sprint #13 – Super Admin | 2025-03-03 | 2025-03-09 | 80
Supper Admin |  |  | 80
Dashboard with the basic stats
Business management (Listing, view, status change)
Template management (Listing, view, status change)
Plan management (Listing, view, status change)
Sprint #14 – Deployment | 2025-03-10 | 2025-03-16 | 60
System Integration & deployment |  |  | 60
Cloud infra setup for the application (on AWS)
Domain binding, DNS and SSL binding.
Deployment of web backend over cloud
Web server configure.
WSGI server configuration.
Installing dependencies.

## Milestone Schedule
Project Release Plan
Milestone No | Sprint | No. of resources | Start Date | End Date | Release No | Milestone Acceptance date | Actual hrs burnt | Status | Acceptance Date
1 | 2 | 2 | 2024-08-26 | 2024-09-08 | ER1 | 2024-09-16
2 | 2 | 2 | 2024-09-09 | 2024-09-22 | ER2 | 2024-09-30
3 | 2 | 2 | 2024-09-23 | 2024-10-06 | ER3 | 2024-10-14
4 | 2 | 2 | 2024-10-07 | 2024-10-20 | ER4 | 2024-10-28
5 | 2 | 2 | 2024-10-21 | 2024-11-03 | ER5 | 2024-11-07

## Summary
Project Start Date | 2024-08-26
Actual End Date | 2024-10-31
Sales Person | ⁠Vishal Sagar Shahi
Revision History
Date | Author | Changes Details | Reference
2024-08-23 | Gaurav Sexena
Resource Allocation
Name | Role On Project | Alignment Date | Resource Released Date
Jashan Dhiman | Developer | 2024-08-22
Bhushan Sharma | Developer | 2024-08-22

## Ghant chart
Gantt Chart
Project Name: | Eye-Refer |  |  |  | Project Start Date |  | 2024-08-26
Project Owner: | Jashan dhiman |  |  |  | Project End Date |  | 2024-10-31
Project Lead : | Gaurav Saxena
|  |  |  | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28
|  |  |  | M1 |  | M2 | M4 | M3 |  | M4 |  | M5
| Resources | Start date | End date | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Admin / Web / Api | Jashan Dhiman | 2024-08-26 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Bhushan Sharma | 2024-08-26 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Desginer | ⁠Yashpal Chaudhary | 2024-08-26 | 31/01/24 | 2024-08-26: 40; 2024-09-02: 20; 2024-09-09: 20
Collection
Deliverables
Acceptance
Review